## Activity & Persons Exposed
TASK SPECIFIC RISK ASSESSMENT
Unit Address: |  |  |  |  | Tel: |  | Unit No. |  | Assessment No. | GRA 62
Assessment Date :
Review Date :
Unit Manager: |  |  |  | Line Manager : |  |  | Assessment completed by :
(Print Name & Job Title) :
Signature :
Copies to : | Operator |  |  | Team-Leader |  | Client | File
A. | Activity and or environment(s) assessed
Exposure of Deluge Pipework for Removal & Repair
General Comments :
Advise those affected of maintenance work/ loss of service.authorised person and Supervisor will initiate Correct PTW. Supervisor will give operative a specific Method Statement / Safe System of Work prior to start which needs to read , understood,agrees and signed on to
B. | Persons Exposed |  | ü | if present. If not applicable - leave blank
ü | Company Employees |  |  |  | ü | Client Employees / Visitors |  | ü | Contractors
| New / Expectant Mums1 |  |  |  | ü | New Starters |  |  | Delivery Personnel
| Elderly (over 65 years) |  |  |  |  | Young Workers2 |  |  | Children2
| People outside of the site |  |  |  |  | Agency Staff |  |  | Special Needs
| Night Workers3 |  |  |  | ü | Lone Workers |  |  | Other (Detail)
1. |  | Separate 'New & Expectant Mothers Risk Assessment' to be completed for each person.
2. |  | Separate 'Children & Young Persons Risk Assessment' to be completed for each person.
3. |  | Separate 'Medical Questionnaire' to be completed for each night worker. Under the 'Working Time Regs' each night worker is entitled
to a free health assessment on request. Initially, this involves completion of a revised copy of the Company's 'Medical Questionnaire'.

## Hazards & Risks
C. | Hazards & Risks :Insert the following into the boxes below: H = High Risk-Likely to occur and serious injuries probable, M = Medium Risk -
Could occur and injuries could possible be serious, L = Low Risk-Unlikely to occur and if it did only minor injury likely. Leave blank if not applicable
Working Practices |  |  | Physical Injury |  |  | Environment
1 |  | Lone Worker | 21 |  | Assault / Violence | 42 | L | Working Outside / Weather
2 | M | Areas Difficult to Access | 22 | L | Portable Equipment Hazards | 43 |  | Confined Spaces
3 |  | Hot Oil | 23 | L | Hand Tools | 44 |  | Access to First - Aid
4 | L | Spillages / Wet Floors | 24 |  | Large Equipment Hazards | 45 |  | Work Overhead
5 |  | Non routine practices | 25 |  | Moving Machine Parts | 46 |  | Excavations
6 |  | Radiological Controlled Areas | 26 | M | Slips, Trips & Falls | 47 |  | Extremes of Temperature
7 |  | Ergonomics | 27 |  | Falls from Heights | 48 |  | Ventilation
8 | H | Isolate / Lock - off | 28 |  | Falling Objects | 49 |  | Access & Egress
Physical Agents |  |  | 29 | M | Transportation Hazards | Training (please tick)
9 |  | Electricity | 30 |  | Sharps | 50 | ü | Task Training
10 | M | Fire | 31 | M | Mobile Plant | 51 | ü | Basic Health & Safety
11 |  | Hot / Cold Objects | 32 |  |  | 52 |  | Display Screen Equipment
12 |  | Noise / Vibration | Hazardous Substances |  |  | 53 | ü | Cleaning / COSHH / Manual Handling
13 |  | Animals | 33 | H | Contact with Chemicals | 54 | ü | Work Instructions
14 |  | Arc Flash / UV Light | 34 |  | Biological Hazards | 55 | ü | Permit To Work
15 | H | Explosion | 35 | H | Dust / Fumes / Gases / Vapours | 56 | ü | Method Statement / S.S.W.
16 | M | Pressure Systems / Gases | 36 |  | Vermin / WeilsDisease | 57 | ü | Toolbox Talk Required
17 |  | Battery Rooms | 37 |  | Zoonotic (Animal to man) Diseases | Other Issues
Handling & Lifting |  |  | 38 |  |  | 58 | ü | Documentation / Signage
18 | M | Handling of Loads | 39 |  |  | 59 | ü | Information / Signage
19 | M | Use of Lifting / Pulling Aids | 40 |  |  | 60 | ü | Equipment
20 |  | Mechanical Lifting Aids | 41 |  |  | 61 | ü | Site Survey

## Control Measures
(d) Significant Risks Identified |  |  | (e) | (f)
(High, Medium or Low Risk) |  |  | Control Measures to be Applied | Responsibilities
No | R | Working Practices |  | By Who | When
2 | M | Areas Difficult to Access | Excavation requires shoring and access and egress ladders | Operative | Each time
4 | L | Spillages / Wet Floors | Water spillages need to be contained and cleared immediately. Wet floor signs need to be displayed whilst the spillage is being cleared and whilst the floor is being wet cleaned, use pump for removal of water and have hose run through to waste water tank. | Operative | Each time
8 | H | Isolate / Lock-off | Permit to work, Double Isolation, Mechanical isolation, Follow Correct Procedure for Isolation and pressure systems | Supervisor | Each time
No | R | Physical Agents |  | By Who | When
10 | M | Fire | Gas Monitoring of Area, Fire Watchman, correct fire extinguisher in Place, In case of fire, employees must know fire evacuation routes and local Fire Muster Point | Supervisor operative | At All Times
15 | H | Explosion | Gas Monitoring of Area , extreme vigilance due to the proximity to the Blending Area | Supervisor operative | At All Times
16 | M | Pressure Systems / Gases | Permit to work, Double Isolation, Mechanical isolation, Follow Correct Procedure for Isolation and pressure systems | Supervisor | Each time
No | R | Handling & Lifting |  | By Who | When
18 | M | Handling of Loads | The most significant loads are likely to be involved in the movement of components in and out of the Excavation. Where the weight of the load is significant, it must be lifted/Lowered Mechanical Aids. | Operative | Each time
(d) Significant Risks Identified |  |  | (e) | (f)
(High, Medium or Low Risk) |  |  | Control Measures to be Applied | Responsibilities
No | R | Physical Injury |  | By Who | When
22 | L | Portable Equipment Hazards | No power tools to be used, intinsically safe equipment only | Operative | Each time
23 | L | Hand Tools | Competent / trained in the use of ,check prior to use
26 | M | Slips, Trips, Falls | Erect 'Caution' sign before commencing work to warn others of the hazard. Ensure all spillages are cleared up immediately. Ensure cabling is not caught/knotted as well as ensuring that it is not obstructing walkways | Operative | Each time
29 | M | Transportation | correct manual handling and transportation for removal of parts to workshop, fork lift truck must have qualified driver and tested for safe use with weight of part | Supervisor operative | Each time
No | R | Hazardous Substances |  | By Who | When
33 | M | Contact with Chemicals | drain system correctly and flush out, wear correct PPE | Operative | Each time
35 | M | Dust/ Fumes/ Gases/ Vapours | correct RPE for welding and Burning mandatory | Operative | Each time
(d) Significant Risks Identified |  |  | (e) | (f)
(High, Medium or Low Risk) |  |  | Control Measures to be Applied | Responsibilities
No | R | Environment |  | By Who | When
42 | M | Working Outside / Weather | Assess weather reports and / or tent out the work area with flame retardent materials | Supervisor operative | Each time
43 | H | Confined Spaces | Gas Monitoring of Area , extreme vigilance due to the proximity to the Blending Area | Supervisor operative | At All Times
46 | M | Excavations | Excavation requires shoring and access and egress ladders | Supervisor operative | At All Times
48 | M | Ventilation | Ventilate and extract weld / burning fumes | Operative | At All Times
49 | M | Access & Egress | access and egress ladders are required for excavation Traffic Barriers may be required. | Supervisor operative | At All Times
No | R | Training (Tick) |  | By Who | When
50 | ü | Task Training | Competency / trade qualifications, manual handling training | General Manager | prior tostart
51 | ü | Basic Health & Safety | All employees should be trained to Level One Basic Health & Safety course | General Manager | Within 3 Months
53 | ü | Cleaning/COSHH/Manual H. | All employees must have access to COSHH assessments for gases and weld consumables etc. must have been trained in their use, the dangers and the precautions to observe. Such training needs to include the use of Personal Protective Equipment. All operaives must be trained in the dangers of slips, trips & falls and the precautions to observe. All staff to receive Manual Handling Training | General Manager | Before work commences
54 | ü | Work Instruction | Service Works Help Desk | Supervisor | Each time
55 | ü | Permit to Work | authorised person and Supervisor will initiate Correct PTW | Supervisor | Each time
56 | ü | Method Statement / SSW | Supervisor will give operative a specific Method Statement / Safe System of Work prior to start which needs to read , understood,agrees and signed on to | Supervisor & Operative | Each time
(d) Significant Risks Identified |  |  | (e) | (f)
(High, Medium or Low Risk) |  |  | Control Measures to be Applied | Responsibilities
No | R | Other Issues (Tick) |  | By Who | When
58 | ü | Documentation / Signage | ESS HSE Guidelines for Employees and Contractors Client Site Procedures Permit To Work for Hot Work and Confined Spaces, HSE (G) IND 258 Safe Working in Confined Space ,HS IND(G) 84 Leptospirosis Are you at Risk | Supervisor | Each time
59 | ü | Information / Signage | Inform Help Desk and Building / Area warden , inform security | Supervisor | Each time
60 | ü | PPE / Equipment | Ensure appropriate PPE and RPE is worn. Check the Chemical Data Sheet for details. Tested and in date equipment - competent in the use of | Supervisor | Each time
61 | ü | Site Survey | Visit Area with Authorised Person prior to Permit Issue for correct Isolation and evaluate Risk and Equipment required | Supervisor | Each time

## Safe System of Work
Task: Exposure of Deluge Pipework for Removal & Repair
Significant Risks: (Detail all High & Medium Risks Here If This SSW is Not Attached to The Risk Assessment)
Is a ‘ Permit To Work’ required? | NO |  | YES | Ref. Number:
Is a designated work instruction required | NO |  | YES | Ref. Number:
Additional Training Required To Undertake this task (if any):
Additional Advice Regarding This Task Available From:
P.P.E. Requirements: Safety Helmet Eye Protection Face Masks Safety Footwear Respirators
High Visibility Clothing Gauntlets Gloves Hearing Defenders Special Gloves All Weather clothing
Other /PPE Required:
Additional Equipment Required:
Who Is Responsible for Management of This Task:
PROCEDURE:
The Pipework will be unbolted from flanges at either end of the leak and removed from the blending area for repair
‘SSW’ Prepared By:(Print) |  | Sign: |  |  | Date ‘SSW’ Last Reviewed: